AI Operating Model Report

Leadership Brief — Meridian Trust Bank

| Field | Detail |
| --- | --- |
| To | Leadership team, Meridian Trust Bank |
| Source | FSOMA Transformation Brief Kit v0.9 (Public Preview) ¦ Engagement: Content & Marketing Operating Model ¦ Retail Banking, Mortgages, Savings, Wealth, Small Business Banking ¦ Engagement ID: MTB-FSOMA-2026-01 |
| Prepared | 3 July 2026 |
| Status | Leadership review draft based on supplied discovery data (synthetic test dataset, not for client delivery) |
| Benchmark mode | Mode 1 — user-provided benchmark register in use; skill default register held as fallback |

# 1. Executive Readout

Where this stands today - The opportunity concentrates in three clusters: regulated-content preparation (WF02, WF03, WF11 — compliance packs, rate-change comms, social review), branch and adviser localisation (WF04, WF05 — highest combined volume at 170 requests/month, and the weakest governance), and manual reporting assembly (WF12, KPI14 at 11 hrs/week from five source systems). - Accountability stays with named human roles across all 14 workflows. AI's role is confined to preparing, routing and reporting; no activity anywhere in this brief assigns AI as Accountable. - Two workflows cannot be sequenced into an AI-supported wave yet: WF04 (no Accountable owner recorded) and WF05 (no Responsible or Accountable owner recorded). Both are held in a Governance Track ahead of Wave 1/2 until an owner is assigned. - 13 of 30 KPIs are Validated; 4 are Needs validation, including the GBP 1.25m productivity savings anchor (KPI27) and the manual-handoffs count (KPI12). Two datasets sit below 60% completeness — Branch request data (38%) and AI usage logs (24%) — and both need remediation before they can support automation or governance reporting. - Regulated-content dependency is High across the estate. Any AI-assisted pilot touching financial promotions (WF03, WF11) needs an approved AI usage and evidence-logging policy before it starts, per Risk R01 and R04.

## Leadership decisions needed

- Assign an Accountable owner for WF04 and both a Responsible and Accountable owner for WF05, before either enters an AI-supported wave (R02).

- Approve the AI usage and evidence-logging policy covering regulated content generation and shadow AI use, before any pilot touching WF03, WF11, T13 or T19 proceeds (R01, R04).

- Agree the revenue-attribution rule linking application completion and lead conversion to funded-account outcomes, before any revenue-growth figure is presented to the Board (R03).

- Approve the four-category benefit reporting split (AI productivity, spend recovery, tooling rationalisation, revenue growth) so this business case is never presented as one blended saving (R07).

- Commission a licence and tooling audit that extends beyond the 20 centrally tracked tools, to reconcile the GBP 0.38m top-down duplication estimate against the GBP 46,800 bottom-up figure this brief can currently evidence.

- Confirm compliance SME capacity for a Wave 1 pilot focused on evidence-pack preparation, not approval decisioning, so Wave 1 does not become a compliance bottleneck itself (R06).

# 2. Current State: Priority Workflow Opportunities

14 workflows were identified from the discovery data. The most repeated automation pattern is AI-assisted preparation against an already-structured rules engine or data source (compliance rules, product rate data, QA checklists) — 8 of 14 workflows fit this pattern directly. The remaining workflows are blocked by a governance gap (2), a data-quality gap (2), or a taxonomy mismatch (1), not by a lack of automation potential.

| Workflow | Impact area | Automation pattern | Benefit |
| --- | --- | --- | --- |
| WF01 Annual planning | Planning | AI-assisted synthesis of channel data into the plan | Shortens 68-day planning-to-launch cycle (KPI04, Partially validated) |
| WF02 Rate change comms | Regulated content | AI drafts rate-change comms from structured rate data (RateCard CMS) | Cuts 9-day cycle toward 5-day target (KPI05, Validated) |
| WF03 Compliance pack prep | Compliance | AI assembles evidence packs from structured compliance rules | Targets 29% rework rate down to 15% and lifts first-submission completeness from 52% to 85% (KPI09, KPI11, Validated) |
| WF04 Branch localisation | Localisation | AI-assisted intake and routing, once a governed intake replaces the mailbox | Held pending RACI fix — highest volume (116/mo) and rework (34%) in the estate (KPI07, KPI10) |
| WF05 Adviser enablement | Channel enablement | AI-assisted content drafting from adviser feedback data | Held pending RACI fix — adviser satisfaction sits at 6.1/10 (KPI29, Validated) |
| WF06 Email/app campaign build | Digital campaign ops | AI builds campaign assets against the existing QA checklist | Structured, high-readiness workflow; supports application completion KPI17 (Validated) |
| WF07 Website updates | Digital content | AI drafts controlled updates to rate and eligibility tables | Cuts 11-day cycle toward 5-day target (KPI08, Validated) |
| WF08 Service script updates | Service comms | AI drafts scripts for review once contact-centre/product ownership is reconciled | Supports consistency behind the 146/qtr confusing-comms complaint count (KPI28, Partially validated) |
| WF09 Mortgage landing pages | Digital acquisition | AI builds and versions landing pages against structured product data | Revenue-linked (KPI18, KPI19) but attribution incomplete — see Section 11 |
| WF10 Wealth webinar content | Events content | AI drafts webinar content for adviser sign-off | Low volume, high-touch approval; limited standalone case |
| WF11 Social compliance review | Compliance | AI pre-screens posts against structured compliance rules | Structured, high-readiness; supports financial promotion incident target (KPI21, Validated) |
| WF12 Quarterly reporting | Reporting | AI assembles the five-source report and drafts the narrative | Cuts 11 hrs/week reporting effort toward 4 hrs/week (KPI14, Partially validated) |
| WF13 Budget reforecasting | Finance ops | AI reconciles marketing and finance taxonomy before reforecast | Needs validation; taxonomy mismatch is the blocker, not workflow structure |
| WF14 Vulnerable customer checks | Governance | AI flags content against a central vulnerable-customer checklist, once defined (R08) | Lifts checks completed from 64% toward 95% target (KPI22, Partially validated) |

Our recommendation - Sequence Wave 1 around the six workflows where automation readiness is High and evidence is Validated (WF02, WF03, WF06, WF07, WF11, plus WF04 once its owner gap is closed). Do not include WF05 in early sequencing until its RACI gap is resolved, even though its impact score is comparable.

# 3. Current State: Operating Accountability (RACI)

The RACI extract covers all 14 workflows. Chief Marketing Officer, Head of Compliance Review and Director of Digital Marketing/Experience are the most frequent Accountable roles. Two workflows carry a governance gap: WF04 has no Accountable owner recorded, and WF05 has neither Responsible nor Accountable recorded.

RACI implication - Across every workflow with a recorded owner, AI's future role is limited to preparing, routing and reporting. The named Accountable owner keeps final decision authority in every case — this brief does not assign AI as Accountable anywhere.

| Activity | Responsible | Accountable |
| --- | --- | --- |
| WF01 Annual product and campaign planning | Product Marketing, Finance Planning | Chief Marketing Officer |
| WF02 Monthly product rate change comms | Product Marketing Operations | Head of Product Marketing |
| WF03 Financial promotion approval pack creation | Marketing Compliance Operations | Head of Compliance Review |
| WF04 Branch-localised campaign requests | Branch Marketing Coordinators | NOT ASSIGNED |
| WF05 Broker/adviser sales enablement content | NOT ASSIGNED | NOT ASSIGNED |
| WF06 Email and app push campaign build | CRM Campaign Operations | Director of Digital Marketing |
| WF07 Website product page updates | Digital Content Team | Director of Digital Experience |
| WF08 Customer service script updates | Contact Centre Content Lead | Customer Operations Director |
| WF09 Mortgage campaign landing pages | Digital Acquisition Team | Mortgage Marketing Director |
| WF10 Wealth webinar content production | Wealth Marketing Team | Head of Wealth Marketing |
| WF11 Social media compliance review | Social Media Manager | Head of Brand and Social |
| WF12 Quarterly performance reporting | Marketing Analytics | Data and Insight Director |
| WF13 Campaign budget reforecasting | Marketing Finance Partner | Finance Business Partner |
| WF14 Vulnerable customer content checks | Customer Inclusion Lead | Customer Outcomes Director |

Our recommendation - Do not carry WF04 or WF05 into the future-state RACI (Section 7) until an owner is assigned to each gap. Treat owner assignment as a precondition for automation, not a parallel workstream — an AI system supporting an activity with no accountable human owner is a governance exposure, not an efficiency gain.

# 4. KPI Model and Evidence Gaps

30 KPIs were extracted from the discovery data. 13 are Validated, 12 are Partially validated, and 4 (KPI03, KPI12, KPI25, KPI27) are Needs validation — including the productivity savings anchor that would otherwise carry the most weight in a leadership case. No KPI baseline has been fabricated: where a figure did not exist in the client data, it is not presented here.

| KPI | Metric | Baseline | Target |
| --- | --- | --- | --- |
| KPI01 | Divisions in scope | 5 count | Maintain 5 |
| KPI02 | Annual marketing/content ops spend | GBP 12.4m | Reduce to GBP 11.2m |
| KPI03 | Untracked local marketing spend | GBP 1.8m | Reduce/reconcile to GBP 0.4m |
| KPI04 | Campaign planning to launch | 68 days | Reduce to 49 days |
| KPI05 | Rate-change comms cycle time | 9 days | Reduce to 5 days |
| KPI06 | Financial promotion approval pack prep | 6 days | Reduce to 2 days |
| KPI07 | Branch-localised campaign request cycle time | 12 days | Reduce to 6 days |
| KPI08 | Website product update cycle time | 11 days | Reduce to 5 days |
| KPI09 | Financial promotion rework rate | 29% | Reduce to 15% |
| KPI10 | Branch localisation rework rate | 34% | Reduce to 18% |
| KPI11 | First submission compliance completeness | 52% | Increase to 85% |
| KPI12 | Manual handoffs per campaign | 27 count | Reduce to 15 |
| KPI13 | Overdue approval steps per regulated campaign | 5.2 count | Reduce to 2 |
| KPI14 | Campaign status reporting effort | 11 hrs/wk | Reduce to 4 hrs/wk |
| KPI15 | Assets with complete compliance metadata | 41% | Increase to 90% |
| KPI16 | Campaigns with single campaign ID across systems | 57% | Increase to 85% |
| KPI17 | Email/app campaign application completion rate | 3.8% | Increase to 4.4% |
| KPI18 | Mortgage lead to funded application conversion | 11.5% | Increase to 12.5% |
| KPI19 | Average funded mortgage value from campaign leads | GBP 236,000 | Maintain / increase |
| KPI20 | Cost per completed savings application | GBP 42 | Reduce to GBP 35 |
| KPI21 | Financial promotion incidents | 3 /qtr | Reduce to 0 |
| KPI22 | Consumer Duty vulnerable customer checks completed | 64% | Increase to 95% |
| KPI23 | AI-assisted workflows in controlled pilot | 0 count | Increase to 5 |
| KPI24 | Teams with named AI workflow champion | 1 of 5 | Increase to 5 of 5 |
| KPI25 | Documented AI use-case guardrails | 2 count | Increase to 8 |
| KPI26 | Tool/licence duplication estimate | GBP 0.38m/yr | Reduce to GBP 0.15m/yr |
| KPI27 | Addressable productivity savings opportunity | GBP 1.25m/yr | Realise GBP 0.75m/yr |
| KPI28 | Customer complaint mentions of confusing comms | 146 /qtr | Reduce to 90 /qtr |
| KPI29 | Adviser content satisfaction | 6.1 /10 | Increase to 8 |
| KPI30 | Branch campaign request satisfaction | 5.6 /10 | Increase to 8 |

Our recommendation - Run a baseline validation sprint on KPI03, KPI12, KPI25 and KPI27 before any of the four sit inside a committed savings number. KPI27 in particular is currently a directional estimate, not a governed figure — see Section 11.

# 5. Technology Role Validation

This is a dependency map for operating-model design, not a confirmed stack recommendation. 20 tools were identified, with a combined run-rate of GBP 211,900/month (GBP 2.54m/yr). 9 are Validated, 8 are Partially validated or Needs validation, and 1 (RatesBot Prototype) is Draft/unverified with no assigned owner.

| Tool | Current Role / Status |
| --- | --- |
| T01 WorkFlow360 | Validated |
| T02 CompliCheck Pro | Validated |
| T03 ContentVault DAM | Partially validated |
| T04 RateCard CMS | Validated |
| T05 BranchRequest Mailbox | Needs validation |
| T06 AdvisorHub Portal | Partially validated |
| T07 CampaignLedger | Needs validation |
| T08 SignalBI | Partially validated |
| T09 CustomerVoice Miner | Needs validation |
| T10 Adobe Experience Manager | Validated |
| T11 Salesforce Marketing Cloud | Validated |
| T12 PolicyDocs SharePoint | Partially validated |
| T13 LLM Sandbox | Needs validation |
| T14 CallScript Studio | Partially validated |
| T15 SocialSafe Archive | Validated |
| T16 SurveyPulse | Validated |
| T17 LoanTrack CRM | Partially validated |
| T18 RatesBot Prototype | Draft/unverified |
| T19 SmartSummary AI | Needs validation |
| T20 Compliance Evidence Spreadsheet | Needs validation |

Our recommendation - Treat the four tools flagged Needs validation with High usage (BranchRequest Mailbox, LLM Sandbox governance, Compliance Evidence Spreadsheet) as priority validation targets — they sit on the critical path for WF03 and WF04, the two highest-rework workflows in the estate. Full cost and dependency detail is in Appendix A.

# 6. Future State: Roadmap

Four phases, sequenced by evidence confidence and AI readiness first, executive visibility second. Timelines are indicative and tied to the organisational complexity already evidenced (5 divisions, High regulatory review dependency, 20-tool estate) — they are not drawn from a client-confirmed delivery plan and should be treated as directional until PMO capacity is confirmed.

Phase 0 — Governance Track (precondition, not a build phase) - WF04 (Branch-localised campaign requests): assign an Accountable owner and minimum required intake fields, per R02. Owner: CMO / Regional Director. - WF05 (Broker/adviser sales enablement content): assign both Responsible and Accountable owners. - Neither workflow enters an AI-supported wave until this phase closes. This overrides the client-stated Wave 1/Wave 2 sequencing for these two workflows specifically — the stated wave reflects volume and impact, not governance readiness, and Mandatory Analytical Behaviour 2 requires the gap to be closed before AI support is designed in.

Phase 1 — Wave 1, months 0-4 (High readiness, Validated evidence) - WF02 Rate change comms, WF03 Compliance pack prep, WF06 Email/app campaign build, WF07 Website updates, WF11 Social compliance review. - All five carry High AI readiness and Validated status. This is the evidence-strongest pilot set and the natural home for the initial KPI23 target (5 AI-assisted workflows in controlled pilot).

Phase 2 — Wave 2, months 4-9 (Medium readiness, mixed evidence) - WF08 Service script updates, WF09 Mortgage landing pages, WF12 Quarterly reporting, WF14 Vulnerable customer checks. - WF04 and WF05 rejoin this phase once Phase 0 closes, assuming their underlying automation readiness (High and Medium respectively) still holds after re-validation.

Phase 3 — Wave 3, months 9-14 (lower readiness or lower volume) - WF01 Annual planning, WF10 Wealth webinar content, WF13 Campaign budget reforecasting. - WF13 also needs the finance/marketing taxonomy reconciled before AI support is designed — treat as a data-readiness gate, not a scheduling delay.

Our recommendation - Do not publish Phase 1-3 dates externally until PMO confirms delivery capacity — these bands are sequencing logic, not a costed project plan.

# 7. Future State: RACI

12 of the 14 workflows carry forward into a future-state RACI. WF04 and WF05 are excluded — carrying a gapped row into a table that implies AI is ready to support it would misstate governance readiness. Both return once Phase 0 (Section 6) closes and Section 3's gap is resolved. In every row below, AI's role is limited to preparation, routing and reporting; the named Accountable owner is unchanged from the current-state RACI and keeps final decision authority. AI is never assigned as Accountable.

| Activity | AI role | Accountable (unchanged) |
| --- | --- | --- |
| WF01 Annual product and campaign planning | AI supports: prepares, routes, reports | Chief Marketing Officer |
| WF02 Monthly product rate change comms | AI supports: prepares, routes, reports | Head of Product Marketing |
| WF03 Financial promotion approval pack creation | AI supports: prepares, routes, reports | Head of Compliance Review |
| WF06 Email and app push campaign build | AI supports: prepares, routes, reports | Director of Digital Marketing |
| WF07 Website product page updates | AI supports: prepares, routes, reports | Director of Digital Experience |
| WF08 Customer service script updates | AI supports: prepares, routes, reports | Customer Operations Director |
| WF09 Mortgage campaign landing pages | AI supports: prepares, routes, reports | Mortgage Marketing Director |
| WF10 Wealth webinar content production | AI supports: prepares, routes, reports | Head of Wealth Marketing |
| WF11 Social media compliance review | AI supports: prepares, routes, reports | Head of Brand and Social |
| WF12 Quarterly performance reporting | AI supports: prepares, routes, reports | Data and Insight Director |
| WF13 Campaign budget reforecasting | AI supports: prepares, routes, reports | Finance Business Partner |
| WF14 Vulnerable customer content checks | AI supports: prepares, routes, reports | Customer Outcomes Director |

Excluded pending governance fix - WF04 Branch-localised campaign requests — excluded until an Accountable owner is assigned (R02). - WF05 Broker/adviser sales enablement content — excluded until Responsible and Accountable owners are both assigned.

# 8. Technology Recommendations

Recommendations refine the client's own recommendation-candidate field already present in the discovery data (Tech_Validation), rather than a generic 'validate everything' pass. 11 tools: Keep. 4: Validate or integrate. 1: Consolidate. 3: Replace. 1: Do not use until governed.

| Tool | Recommendation | Reason |
| --- | --- | --- |
| T01 WorkFlow360 | Keep, enforce intake fields | Main workflow system but email handoffs still leak out |
| T02 CompliCheck Pro | Keep, integrate upstream | Rules engine useful but evidence pack upload is manual |
| T03 ContentVault DAM | Keep, enforce metadata | Only 41% compliance metadata complete |
| T04 RateCard CMS | Keep | Strong structured data source |
| T05 BranchRequest Mailbox | Replace with governed intake | Unstructured mailbox creates RACI and data quality issues |
| T06 AdvisorHub Portal | Validate / integrate | Usage data incomplete |
| T07 CampaignLedger | Rebuild taxonomy | Finance taxonomy differs from marketing |
| T08 SignalBI | Keep, automate narrative | Weekly reporting still manually compiled |
| T09 CustomerVoice Miner | Validate before scaling | Could support vulnerable customer checks, but taxonomy unproven |
| T10 Adobe Experience Manager | Keep | Core site platform |
| T11 Salesforce Marketing Cloud | Keep with governance | Strong data but journey documentation inconsistent |
| T12 PolicyDocs SharePoint | Govern / clean | Multiple policy copies in circulation |
| T13 LLM Sandbox | Govern before use | Ad hoc pilot use, unclear audit logging |
| T14 CallScript Studio | Keep if integrated | No direct compliance system link |
| T15 SocialSafe Archive | Keep | Works but comments are not structured into recommendations |
| T16 SurveyPulse | Keep | Useful for adoption feedback |
| T17 LoanTrack CRM | Integrate for revenue attribution | Attribution to funded applications incomplete |
| T18 RatesBot Prototype | Do not use until governed | No owner, not approved for production |
| T19 SmartSummary AI | Consolidate with LLM Sandbox | Overlap with LLM Sandbox and SignalBI narrative layer |
| T20 Compliance Evidence Spreadsheet | Replace with system workflow | Operationally critical but manual |

Our recommendation - Prioritise three actions: replace BranchRequest Mailbox with a governed intake (closes the WF04 data-quality root cause), consolidate SmartSummary AI into LLM Sandbox or SignalBI's narrative layer (closes part of the tooling-rationalisation gap in Section 11), and govern LLM Sandbox before any further ad hoc use (closes R04). Full cost and workflow-dependency detail is in Appendix A.

# 9. KPI Model and Benchmarks

BM-USER-002 (McKinsey, 5-15% of marketing spend) applies to Category 1 modelling only — see Section 11. No verified benchmark exists at KPI level for the operational metrics below; targets are the client's own governed targets, not benchmark-derived.

| KPI | Metric | Baseline | Target | Evidence |
| --- | --- | --- | --- | --- |
| KPI01 | Divisions in scope | 5 count | Maintain 5 | Validated |
| KPI02 | Annual marketing/content ops spend | GBP 12.4m | Reduce to GBP 11.2m | Partially validated |
| KPI03 | Untracked local marketing spend | GBP 1.8m | Reduce/reconcile to GBP 0.4m | Needs validation |
| KPI04 | Campaign planning to launch | 68 days | Reduce to 49 days | Partially validated |
| KPI05 | Rate-change comms cycle time | 9 days | Reduce to 5 days | Validated |
| KPI06 | Financial promotion approval pack prep | 6 days | Reduce to 2 days | Validated |
| KPI07 | Branch-localised campaign request cycle time | 12 days | Reduce to 6 days | Partially validated |
| KPI08 | Website product update cycle time | 11 days | Reduce to 5 days | Validated |
| KPI09 | Financial promotion rework rate | 29% | Reduce to 15% | Validated |
| KPI10 | Branch localisation rework rate | 34% | Reduce to 18% | Partially validated |
| KPI11 | First submission compliance completeness | 52% | Increase to 85% | Validated |
| KPI12 | Manual handoffs per campaign | 27 count | Reduce to 15 | Needs validation |
| KPI13 | Overdue approval steps per regulated campaign | 5.2 count | Reduce to 2 | Validated |
| KPI14 | Campaign status reporting effort | 11 hrs/wk | Reduce to 4 hrs/wk | Partially validated |
| KPI15 | Assets with complete compliance metadata | 41% | Increase to 90% | Validated |
| KPI16 | Campaigns with single campaign ID across systems | 57% | Increase to 85% | Partially validated |
| KPI17 | Email/app campaign application completion rate | 3.8% | Increase to 4.4% | Validated |
| KPI18 | Mortgage lead to funded application conversion | 11.5% | Increase to 12.5% | Partially validated |
| KPI19 | Average funded mortgage value from campaign leads | GBP 236,000 | Maintain / increase | Partially validated |
| KPI20 | Cost per completed savings application | GBP 42 | Reduce to GBP 35 | Partially validated |
| KPI21 | Financial promotion incidents | 3 /qtr | Reduce to 0 | Validated |
| KPI22 | Consumer Duty vulnerable customer checks completed | 64% | Increase to 95% | Partially validated |
| KPI23 | AI-assisted workflows in controlled pilot | 0 count | Increase to 5 | Validated |
| KPI24 | Teams with named AI workflow champion | 1 of 5 | Increase to 5 of 5 | Validated |
| KPI25 | Documented AI use-case guardrails | 2 count | Increase to 8 | Needs validation |
| KPI26 | Tool/licence duplication estimate | GBP 0.38m/yr | Reduce to GBP 0.15m/yr | Partially validated |
| KPI27 | Addressable productivity savings opportunity | GBP 1.25m/yr | Realise GBP 0.75m/yr | Needs validation |
| KPI28 | Customer complaint mentions of confusing comms | 146 /qtr | Reduce to 90 /qtr | Partially validated |
| KPI29 | Adviser content satisfaction | 6.1 /10 | Increase to 8 | Validated |
| KPI30 | Branch campaign request satisfaction | 5.6 /10 | Increase to 8 | Partially validated |

Our recommendation - Anchor the Wave 1 business case on the 13 Validated KPIs only (KPI01, KPI05, KPI06, KPI08, KPI09, KPI11, KPI13, KPI15, KPI17, KPI21, KPI23, KPI24, KPI29). Present the remaining 17 as directional until their evidence status improves — do not average a Validated and a Needs-validation KPI into a single confidence rating.

# 10. Impact vs Effort

14 workflows plotted on business impact against implementation effort, using the impact and effort scores already present in the discovery data (used directly, not re-derived). Numbered markers with a legend are used throughout — the workflow count alone (14, above the 8-item threshold) triggers this per the chart-safe formatting rule, before collision or label-length are even considered.

Our recommendation - Quick Wins (WF02, WF06, WF08, WF11, WF12) plus the two gold-marked governance-gap workflows (WF04, WF05, once resolved) form the natural Wave 1/2 pool. WF03 and WF14 carry the highest impact scores in the estate (10 and 9) but sit at Medium-High effort — treat both as Major Projects that justify dedicated pilot resourcing rather than folding them into a general Wave 1 sprint.

# 11. Commercial Model

Four benefit categories, never blended into one headline figure, per Risk R07. Each category states its own baseline, evidence level and cross-check result.

## Benchmark governance for this model

Mode 1 (user-provided register) applies. BM-USER-002 (McKinsey & Company, 'The economic potential of generative AI', 5-15% of marketing spend, Primary verified, Client-facing, checked against all ten client-facing conditions) is the load-bearing benchmark for Category 1. Three other rows in the user-provided register were assessed and excluded from client-facing use: BMK-U001 (Secondary/internal, Internal challenge only — conversion-uplift figure, excluded from Category 4), BMK-U003 (Draft/unverified, missing source URL — excluded entirely), and BMK-U004 (Draft/unverified, no public source — excluded entirely, would otherwise have supported a compliance cycle-time claim in Category 1 for WF03/WF11).

## 1. AI productivity

Baseline: GBP 12.4m annual marketing/content ops spend (Partially validated, KPI02). Benchmark: BM-USER-002, 5-15% of marketing spend, Primary verified. Functional scope matches directly — this is a marketing-function benchmark applied to marketing spend, not a general figure borrowed across scope.

| Scenario | Basis | Annual value | Note |
| --- | --- | --- | --- |
| Conservative | 5% (low end of range) | GBP 0.62m | Highest-automation-readiness workflows only (Wave 1 set) |
| Base | 10% (midpoint) | GBP 1.24m | Applied across medium-to-high readiness workflows |
| Optimistic | 15% (high end) | GBP 1.86m | Upper bound; faster-than-typical adoption, not the planning number |

Cross-check: Top-down (base case, GBP 1.24m) converges with Client-stated (KPI27, GBP 1.25m addressable, target realise GBP 0.75m — Needs validation, Low confidence). The two figures sit under 1% apart despite being built independently: one from a public benchmark applied to total spend, the other from the client's own directional model. Bottom-up: not evidenced — no per-workflow costed automation-saving sum exists in the discovery data (KPI27's own note flags this: 'needs benchmark and workflow spend allocation'). Benchmark-derived raw: 5-15%.

Evidence caveat - The GBP 12.4m spend base itself is Partially validated (it excludes some branch and broker-local activity, per KPI02 and the untracked-spend line in Category 2). A spend base validation should run alongside baseline confirmation before this becomes a committed number. - Payback in months cannot be calculated. Implementation cost estimate requires tooling/licensing, integration or build cost, and change-management/training cost — none of the three are present in the discovery data. Current tool run-rate (GBP 211,900/month) is operating cost, not implementation cost, and is not substituted here. Payback is directionally indicative only until a costed implementation plan exists.

## 2. Spend recovery

Baseline: GBP 1.8m estimated untracked local spend (Current-state summary; KPI03, Needs validation, Low confidence), sourced from a branch PO sample outside the central coding model. Target: reduce/reconcile to GBP 0.4m. Addressable recovery: up to GBP 1.4m/yr, point estimate, not a benchmark range. This is a finance and governance exercise — no AI productivity benchmark is applied here, even though BM-USER-002 is available, because it measures a different thing.

## 3. Tooling rationalisation

Top-down (client-stated): KPI26, GBP 0.38m/yr duplication estimate (Partially validated). Bottom-up: GBP 46,800/yr — the annualised run-rate of SmartSummary AI (T19, GBP 3,900/month), the only tool in the 20-tool register explicitly flagged as overlapping with named others (LLM Sandbox T13, SignalBI T08 narrative layer).

Cross-check: Diverges - GBP 0.38m top-down is roughly eight times GBP 46,800 bottom-up. Likely cause: the client's duplication estimate extends beyond the 20 centrally tracked tools into branch and broker-local tooling that is not yet mapped in this register — the same visibility gap that produces the GBP 1.8m untracked spend line in Category 2. A second possible cause: further overlaps exist among the tools currently marked Partially validated or Needs validation (T09, T14, T20) that have not yet been formally flagged as duplicative. - Validation action: commission a licence and tooling audit that extends beyond the central register before governing the GBP 0.38m figure (carried to Section 14).

## 4. Revenue growth

Revenue-linked KPIs are present: KPI17 (email/app application completion, 3.8% to 4.4%, Validated), KPI18 (mortgage lead-to-funded conversion, 11.5% to 12.5%, Partially validated), KPI19 (average funded mortgage value, GBP 236,000, maintain/increase, Partially validated). This satisfies the condition for a revenue-growth case to exist.

Quantification withheld pending R03 - No verified benchmark is available to convert these KPI movements into a currency figure — BMK-U001 (the only benchmark scoped to conversion uplift) is Secondary/internal, Internal challenge only, and is excluded from this client-facing model. - Risk R03 states plainly: application completion does not equal funded account revenue. KPI18 and KPI19 are both flagged 'attribution incomplete.' Presenting a monetary revenue figure before Finance agrees the attribution rule would overclaim. - Directional statement only: a revenue-growth case exists in principle, tied to KPI17/18/19 movement, but no monetary figure is presented until R03 is resolved.

Primary planning basis - AI productivity, Base scenario (GBP 1.24m/yr) is recommended as the primary planning number. It is the only category with genuine benchmark support across a range, and it is the category where an independently-built client-stated figure (KPI27) converges with the benchmark-derived top-down calculation. It remains conditional on validating the GBP 12.4m spend base and on closing the WF04/WF05 governance gap, since both Wave 1 candidates outside the governance track carry the strongest evidence behind this figure.

# 12. Risk Flags and Validation Needed

Eight risks were supplied in the client's own Risk & Assumption Register and are carried forward by their original ID, not restated as new findings. Three further gaps were identified during this analysis and are added below the register.

| ID | Risk | Severity | Decision needed | Owner |
| --- | --- | --- | --- | --- |
| R01 | AI-generated financial promotions could bypass required compliance review | High | Approve AI usage policy before any regulated content pilot | Chief Risk Officer |
| R02 | Automation could accelerate incomplete or non-compliant branch requests | High | Assign WF04 accountable owner and minimum fields | CMO / Regional Director |
| R03 | Revenue model may overclaim because application completion does not equal funded account revenue | High | Agree revenue attribution rule before leadership case | Finance Director |
| R04 | Shadow AI usage in marketing and adviser teams is not auditable | High | Approve AI guardrails and logging policy | Technology Risk |
| R05 | Multiple campaign ID schemes prevent end-to-end reporting | Medium | Approve campaign ID standard | PMO Lead |
| R06 | Compliance team capacity may bottleneck Wave 1 rather than improve it | Medium | Confirm compliance SME capacity for pilot | Head of Compliance Review |
| R07 | Cost reduction target may blend productivity, spend leakage, and tool rationalisation | High | Approve reporting split before business case is shared | Finance Director |
| R08 | Customer vulnerability checks remain inconsistent across channels | High | Define vulnerable customer content checklist | Customer Outcomes Director |

## Additional flags identified in this analysis

- RACI governance gap, WF05 (Broker/adviser sales enablement content): both Responsible and Accountable are unassigned. Not covered by an existing risk ID — flagged here as a new governance gap alongside R02's coverage of WF04.

- Tooling-rationalisation scope gap: the GBP 0.38m top-down duplication estimate (KPI26) diverges roughly eightfold from the GBP 46,800 bottom-up figure this brief can evidence (Section 11, Category 3). Scope likely extends beyond the 20 centrally tracked tools.

- Data-foundation gap, two datasets below 60% completeness: Branch request data (38%, Low confidence) and AI usage logs (24%, Low confidence). See Section 13.

# 13. Data Foundation Readiness

11 datasets were supplied in the client's Data Inventory. This informs KPI confidence, roadmap sequencing, automation-readiness scoring, reporting feasibility, the data-foundation risk flags above, and commercial-model confidence directly — it is not background context.

| Dataset | System of record | Completeness | Cadence | Confidence |
| --- | --- | --- | --- | --- |
| Campaign master list | WorkFlow360 | 74% | Daily | Medium |
| Product rate and eligibility data | RateCard CMS | 93% | Daily | High |
| Compliance review decisions | CompliCheck Pro | 89% | Daily | High |
| Branch request data | BranchRequest Mailbox | 38% | Ad hoc | Low |
| Adviser portal usage | AdvisorHub Portal | 61% | Weekly | Medium |
| Marketing spend and PO data | Finance export | 68% | Monthly | Medium |
| Digital campaign performance | Salesforce Marketing Cloud / Analytics | 86% | Daily | High |
| Mortgage application outcome data | LoanTrack CRM | 72% | Weekly | Medium |
| Website analytics | Web analytics | 91% | Daily | High |
| Complaints and customer outcome data | Customer Experience platform | 66% | Monthly | Medium |
| AI usage logs | LLM Sandbox | 24% | Ad hoc | Low |

How this changes the brief - KPI confidence: Branch request data (38%) is the direct evidentiary basis for KPI07, KPI10 and KPI30, all correctly tagged Partially validated or worse in Section 4 rather than Validated, because the source dataset itself is below 60% complete. - Roadmap sequencing: AI usage logs at 24% completeness is a second reason (alongside R04's audit-logging gap) that any AI governance milestone (KPI25) sits in Wave 2/3, not Wave 1 — the underlying data isn't there yet to govern against. - Automation-readiness scoring: WF04's automation readiness is scored High in Section 2, but that score sits on a 38%-complete dataset. Treat the readiness score as provisional until intake data quality improves, independent of the RACI gap already blocking WF04. - Reporting feasibility: Marketing spend and PO data at 68% completeness is the direct constraint behind KPI02's Partially validated tag and the GBP 1.8m untracked-spend estimate's Low confidence in Category 2 of the commercial model. - Commercial model confidence: KPI27 (the GBP 1.25m productivity anchor) sits partly on the same incomplete spend and campaign-ID data (Campaign master list, 74%; Marketing spend and PO data, 68%), which is a second reason — alongside the missing workflow-spend allocation already noted in Section 11 — that it remains Needs validation.

# 14. Recommended Next Steps

Every material gap raised in Section 1 and Section 11 is closed here as a named, owned action. Checked against all seven mandatory gap types.

| # | Action | Owner | Gap type closed |
| --- | --- | --- | --- |
| 1 | Assign an Accountable owner for WF04 and both Responsible and Accountable owners for WF05, and re-run their automation-readiness score once assigned. | CMO / Regional Director | RACI gap |
| 2 | Approve the AI usage and evidence-logging policy before any pilot touches WF03, WF11, T13 (LLM Sandbox) or T19 (SmartSummary AI). | Chief Risk Officer / Technology Risk | Risk-register gap (R01, R04) |
| 3 | Agree the revenue-attribution rule linking KPI17/KPI18 conversion to funded-account outcomes before any monetary revenue-growth figure is presented. | Finance Director | Revenue-growth gap (R03) |
| 4 | Approve the four-category benefit reporting split before this business case reaches the Board. | Finance Director | Benefit-category reporting decision (R07) |
| 5 | Commission a licence and tooling audit extending beyond the 20 centrally tracked tools to reconcile the GBP 0.38m vs GBP 46,800 duplication estimate. | Procurement | Tooling-rationalisation scope gap |
| 6 | Run a baseline validation sprint on KPI03, KPI12, KPI25 and KPI27, and on the GBP 12.4m spend base, before any of them anchor a committed figure. | PMO / Transformation Lead | Benchmark / baseline gap |
| 7 | Fund remediation for Branch request data (38% complete) and AI usage logs (24% complete) before they support Wave 1/2 automation or AI-governance reporting. | Regional Marketing / Technology Risk | Data-foundation gap |
| 8 | Close the remaining risk-register decisions: campaign ID standard (R05), compliance SME capacity confirmation (R06), and vulnerable-customer content checklist (R08). | PMO Lead / Head of Compliance Review / Customer Outcomes Director | Risk-register gap |
| 9 | Cost the Wave 1 implementation plan (tooling/licensing, integration, change management) so payback in months can be calculated for the AI productivity base case. | Transformation Lead / Finance | Commercial model completeness |

# Appendix A: Full Technology Stack

Complete 20-tool register with cost, usage, workflow dependency and risk notes, moved here from Section 5 / Section 8 per the six-column table rule (this table has 8 decision-relevant columns and does not compress cleanly to fewer without losing decision-critical information).

| ID | Tool | Category | Monthly cost | Usage | Status | Workflow dependency | Risk / notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| T01 | WorkFlow360 | Workflow orchestration | GBP 21,400 | High | Validated | WF02,WF03,WF06,WF07 | Main workflow system but email handoffs still leak out |
| T02 | CompliCheck Pro | Financial promotion review | GBP 18,600 | High | Validated | WF03,WF11,WF14 | Rules engine useful but evidence pack upload is manual |
| T03 | ContentVault DAM | DAM / asset storage | GBP 12,800 | Medium | Partially validated | WF04,WF07,WF10 | Only 41% compliance metadata complete |
| T04 | RateCard CMS | Product rate content mgmt | GBP 9,600 | High | Validated | WF02,WF07 | Strong structured data source |
| T05 | BranchRequest Mailbox | Branch request intake | GBP 0 | High | Needs validation | WF04 | Unstructured mailbox creates RACI and data quality issues |
| T06 | AdvisorHub Portal | Sales enablement | GBP 11,200 | Medium | Partially validated | WF05 | Usage data incomplete |
| T07 | CampaignLedger | Budget tracking | GBP 7,200 | Medium | Needs validation | WF13 | Finance taxonomy differs from marketing |
| T08 | SignalBI | Marketing reporting BI | GBP 15,200 | Medium | Partially validated | WF12 | Weekly reporting still manually compiled |
| T09 | CustomerVoice Miner | Complaint analysis | GBP 8,300 | Low | Needs validation | WF14 | Could support vulnerable customer checks, but taxonomy unproven |
| T10 | Adobe Experience Manager | CMS | GBP 26,400 | High | Validated | WF07,WF09 | Core site platform |
| T11 | Salesforce Marketing Cloud | CRM campaign platform | GBP 39,200 | High | Validated | WF06,WF09 | Strong data but journey documentation inconsistent |
| T12 | PolicyDocs SharePoint | Policy/document store | GBP 0 | High | Partially validated | WF03,WF14 | Multiple policy copies in circulation |
| T13 | LLM Sandbox | Generative AI / LLM | GBP 4,800 | Low | Needs validation | WF03,WF04,WF12 | Ad hoc pilot use, unclear audit logging |
| T14 | CallScript Studio | Contact centre script tool | GBP 6,700 | Medium | Partially validated | WF08 | No direct compliance system link |
| T15 | SocialSafe Archive | Social compliance archive | GBP 5,900 | High | Validated | WF11 | Works but comments are not structured into recommendations |
| T16 | SurveyPulse | Satisfaction survey | GBP 2,200 | Medium | Validated | KPI29/KPI30 | Useful for adoption feedback |
| T17 | LoanTrack CRM | Mortgage CRM | GBP 18,500 | Medium | Partially validated | WF09 | Attribution to funded applications incomplete |
| T18 | RatesBot Prototype | Internal automation | GBP 0 | Low | Draft/unverified | WF02 | No owner, not approved for production |
| T19 | SmartSummary AI | AI summarisation | GBP 3,900 | Low | Needs validation | WF12 | Overlap with LLM Sandbox and SignalBI narrative layer |
| T20 | Compliance Evidence Spreadsheet | Manual evidence tracker | GBP 0 | High | Needs validation | WF03 | Operationally critical but manual |

# Appendix B: Benchmark Register Validation Log

Per Mandatory Analytical Behaviour 7, Mode 1: the user-provided register (4 rows, User_Benchmark_Register) was validated against the 15-field schema and the ten client-facing conditions before any row was used.

| ID | Metric | Value | Evidence status | Allowed use | Outcome |
| --- | --- | --- | --- | --- | --- |
| BMK-U001 | Conversion rate uplift | 0.4-0.8 pp | Secondary/internal | Internal challenge only | Excluded from client-facing Category 4. No source URL beyond a placeholder; internal-only by the user's own label, honoured as such. |
| BMK-U002 | Marketing productivity uplift | 5-15% of spend | Primary verified | Client-facing | Accepted. Independently checked: all 10 client-facing conditions present. Same figure as the skill's own default register (BM-DEFAULT-001) — Mode 1 uses the user-provided row per the skill's precedence rule. |
| BMK-U003 | Time saved per marketer | 6.1 hrs/week | Draft/unverified | Client-facing (as labelled) | Excluded. Missing source_url and a traceable primary source. The user's Client-facing label was not taken at face value — evidence_status of Draft/unverified fails the ten-condition test regardless. |
| BMK-U004 | Compliance cycle-time reduction | 20-30% | Draft/unverified | Client-facing (as labelled) | Excluded. No public source provided ('User estimate'). Would have supported a WF03/WF11 cycle-time claim in Category 1 — Mode 3 wording applies instead wherever this metric is discussed. |

Result: 1 of 4 user-provided rows accepted for client-facing use (25%). 3 excluded — 1 for Internal challenge only labelling, 2 for Draft/unverified evidence status regardless of how the row itself was labelled. The skill's own default register (references/default-benchmark-register.md) holds the same accepted figure as a fallback and was not otherwise needed for this run.